## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-1 | Setup Python, SQLite & Define Text Type (Customer Feedback) | MUST HAVE | NA | RAJYALAKSHMI | 3- Completed
S1 | S1 | US-2 | Implement Text Reading, Chunking & Rule-Based Scoring | MUST HAVE | NA | RAJYALAKSHMI | 3- Completed
S1 | S1 | US-3 | Implement Database Storage & Processing Flow | MUST HAVE | NA | RAJYALAKSHMI | 3- Completed
S2 | S2 | US-4 | Develop Text Breaker for splitting large text datasets | MUST HAVE | US-3 | RAJYALAKSHMI | 3- Completed
S2 | S2 | US-5 | Implement Parallel Text Loader using multiprocessing | MUST HAVE | US-4 | RAJYALAKSHMI | 3- Completed
S2 | S2 | US-6 | Test Text Loader with large CSV text files | MUST HAVE | US-5 | RAJYALAKSHMI | 3- Completed
S3 | S3 | US-7 | Implement large-scale data handling (50,000+ records) using chunking logic | MUST HAVE | US-5 | RAJYALAKSHMI | 3- Completed
S3 | S3 | US-8 | Enhance NLP engine with business, financial, and news-specific vocabulary | MUST HAVE | US-4 | RAJYALAKSHMI | 3- Completed
S3 | S3 | US-9 | Develop interactive Dashboard UI with Chart.js for data visualization | SHOULD HAVE | US-7 | RAJYALAKSHMI | 3- Completed
S4 | S4 | US-10 | Implement SQLite database for storing processed text results | MUST HAVE | US-3 | RAJYALAKSHMI | 3- Completed
S4 | S4 | US-11 | Add email reporting (simulation) | MUST HAVE | US-10 | RAJYALAKSHMI | 3- Completed
S4 | S4 | US-12 | Optimize performance using Sets | MUST HAVE | US-2 | RAJYALAKSHMI | 3- Completed
S4 | S4 | US-13 | Validate performance improvement | SHOULD HAVE | US-12 | RAJYALAKSHMI | 3- Completed
S4 | S4 | US-14 | Validate performance improvement | SHOULD HAVE | US-13 | RAJYALAKSHMI | 3- Completed
Note on F1: ====== ID#AAAB0a0FiYQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-1 | T-1 | Introduction of Project | 2026-02-10 | 2026-02-10 | All | Planning | 3-Completed | 1
US-1 | T-2 | Python Setup &SQLite installation | 2026-02-11 | 2026-02-11 | All | Setup | 3-Completed | 1
US-2 | T-3 | Learn Text Handling& Multiprocessing Concepts | 2026-02-12 | 2026-02-13 | All | Learning | 3-Completed | 2
US-2 | T-4 | Design Processing Flow & Module Structure | 2026-02-14 | 2026-02-15 | All | Design | 3-Completed | 2
US-3 | T-5 | Implement Text Reading, Chunking & Scoring | 2026-02-16 | 2026-02-16 | All | Coding | 3-Completed | 3
US-3 | T-6 | Build Main Processing Pipeline &Database Storage | 2026-02-17 | 2026-02-18 | All | Coding | 3-Completed | 3
US-4 | T-7 | Implement text splitting logic | 2026-02-24 | 2026-02-25 | All | Coding | 3-Completed | 3
US-4 | T-8 | Implement batch text processing | 2026-02-26 | 2026-02-27 | All | Coding | 3-Completed | 2
US-5 | T-9 | Implement multiprocessing loader | 2026-02-28 | 2026-03-01 | All | Coding | 3-Completed | 3
US-5 | T-10 | Integrate loader with text breaker | 2026-03-02 | 2026-03-03 | All | Coding | 3-Completed | 2
US-6 | T-11 | Test system with large text dataset | 2026-03-04 | 2026-03-05 | All | Coding | 3-Completed | 2
US-6 | T-12 | Measure performance improvement | 2026-03-06 | 2026-03-06 | All | Coding | 3-Completed | 2
US-7 | T-13 | Implement ThreadPoolExecutor for concurrent data chunking | 2026-03-15 | 2026-03-17 | All | Coding | 3-Completed | 4
US-7 | T-14 | Optimize memory management for front-end table rendering (500 row limit) | 2026-03-18 | 2026-03-18 | All | Coding | 3-Completed | 5 | bar: Day 2
US-8 | T-15 | Expand NLP dictionary with news/business keywords and intensifier logic | 2026-03-19 | 2026-03-19 | All | Research | 3-Completed | 3
US-9 | T-16 | Integrate Chart.js for Sentiment Distribution and Score Frequency graphs | 2026-03-20 | 2026-03-21 | All | Coding | 3-Completed | 5
US-9 | T-17 | Implement CSV/Excel export functionality for filtered search results | 2026-03-21 | 2026-03-23 | All | Coding | 3-Completed | 4
US-10 | T-18 | Setup SQLite DB & save results | 2026-03-27 | 2026-03-28 | All | planning | 3-Completed | 2
US-11 | T-19 | Implement email simulation | 2026-03-28 | 2026-03-28 | All | Coding | 3-Completed | 2
US-12 | T-20 | Replace list with set optimization | 2026-03-29 | 2026-03-29 | All | Coding | 3-Completed | 2
US-13 | T-21 | Measure performance (list vs set) | 2026-03-29 | 2026-03-29 | All | testing | 3-Completed | 2
Note on D2: ====== ID#AAAB0a0FiYc Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAAB0a0FiYo Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAAB0a0FiYw Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAAB0a0FiZE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAAB0a0FiY0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAAB0a0FiZI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAAB0a0FiYg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAAB0a0FiYY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAAB0a0FiY4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAAB0a0FiYU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAAB0a0FiYE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAAB0a0FiYI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAAB0a0FiY8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAAB0a0FiYM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAAB0a0FiZA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAAB0a0FiYk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAAB0a0FiYs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day-5 | Understanding multiprocessing concepts | Studied examples and clarified session
S1 | Day-9 | Minor database error | Debugged and fixed
S2 | Day-2 | Parallel processing errors during testing | Debugged multiprocessing code
S2 | Day-4 | Performance testing with large files slow | Optimized text splitting logic
S3 | Day-4 | Browser freezing when attempting to render 50,000+ rows in the HTML table | Implemented DOM row-capping (500 rows) and offloaded full data to CSV expor
S3 | Day-10 | Git "non-fast-forward" error during final deployment push | Performed git pull --allow-unrelated-histories and forced upstream tracking
S4 | Day-2 | Email sending blocked due to security restrictions | Implemented SMTP simulation instead of real email
S4 | Day-3 | Slow performance using list lookup | Replaced list with set for faster processing
S4 | Day-4 | Errors while storing large data in database | Fixed using try-except and optimized DB logic

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2026-02-10 | 2026-02-18 | Rajyalakshmi | Start designing architecture before coding | Stop coding without planning | Continue modular programming approach | Practice advanced parallel processing in next milestone
2 | S2 | 2026-02-24 | 2026-03-06 | Rajyalakshmi | Start writing optimized parallel code | Stop testing with very small datasets | Continue modular coding practice | Improve performance testing in next sprint
3 | S3 | 2026-03-15 | 2026-03-23 | Rajyalakshmi | Documenting system limitations (sarcasm/context) | Manually processing small datasets sequentially | Using concurrent.futures for high-volume tasks | Finalized 1.5x speedup benchmarks
4 | S4 | 2026-03-27 | 2026-03-29 | Rajyalakshmi | Start using database storage and performance optimization | Stop using inefficient list-based lookup | Continue parallel processing and modular design | Implemented SQLite storage, set optimization, and email simulation
5
6
7